## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project initiation and requirement analysis | MUST HAVE | No Dependency | Jaya Varsini | Completed
S1 | S1 | US-002 | Setup React frontend and UI framework | MUST HAVE | Node.js | Jaya Varsini | Completed
S2 | S2 | US-003 | Setup FastAPI backend and API structure | MUST HAVE | Python | Jaya Varsini | Completed
S2 | S2 | US-004 | File upload system for chat/audio | MUST HAVE | FastAPI | Jaya Varsini | Completed
S3 | S3 | US-005 | Implement Whisper transcription module | SHOULD HAVE | faster-whisper | Jaya Varsini | Completed
S3 | S3 | US-006 | LLM scoring engine (empathy, compliance, resolution) | MUST HAVE | Groq API | Jaya Varsini | Completed
S4 | S4 | US-007 | Compliance violation detection and suggestions | MUST HAVE | LLM | Jaya Varsini | Completed
S5 | S5 | US-008 | RAG pipeline using FAISS for policy retrieval | SHOULD HAVE | FAISS | Jaya Varsini | Completed
S6 | S6 | US-009 | Dashboard UI with analytics and charts | MUST HAVE | Recharts | Jaya Varsini | Completed
S7 | S7 | US-010 | Alerts system for compliance issues | SHOULD HAVE | Backend logic | Jaya Varsini | Completed
S8 | S8 | US-011 | Report generation (PDF & Excel) | MUST HAVE | Report module | Jaya Varsini | Completed
S8 | S8 | US-012 | Deployment (Netlify + Render) | MUST HAVE | Hosting | Jaya Varsini | Completed

## Sprint 1 Backlog
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Est. Hours | Day1 | Day2 | Day3 | Day4 | Day5
US-001 | 1 | Requirement analysis | Day 1 | Day 2 | Jaya Varsini | Planning | Completed | 4 | 1 | 1 | 1 | 1 | 0
US-002 | 2 | Setup React project | Day 3 | Day 4 | Jaya Varsini | Development | Completed | 6 | 2 | 2 | 1 | 1 | 0
US-002 | 3 | UI design (Dashboard layout) | Day 4 | Day 5 | Jaya Varsini | Design | Completed | 5 | 1 | 1 | 1 | 1 | 1

## Sprint 2 Backlog
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Est. Hours
US-003 | 4 | Setup FastAPI backend | Day 6 | Day 7 | Jaya Varsini | Development | Completed | 6
US-004 | 5 | Implement file upload API | Day 7 | Day 9 | Jaya Varsini | Development | Completed | 8

## Sprint 3 Backlog
US ID | Task ID | Task Description | Start Date | End Date | Activity | Status
US-005 | 6 | Whisper integration | Day 10 | Day 12 | AI Integration | Completed
US-006 | 7 | LLM scoring logic | Day 12 | Day 14 | AI Development | Completed

## Sprint 4-8 Summary
Sprint | Task Description
Sprint 4 | Compliance detection and suggestions
Sprint 5 | RAG implementation using FAISS
Sprint 6 | Dashboard analytics and visualization
Sprint 7 | Alerts system
Sprint 8 | Report generation and deployment

## Standup Log
Sprint | Day | Impediment | Action Taken
Sprint 1 | Day 2 | Lack of clarity in requirements | Discussed with mentor and finalized scope
Sprint 2 | Day 7 | Backend API errors | Debugged and fixed API routing
Sprint 3 | Day 11 | Whisper transcription issues | Added fallback handling
Sprint 4 | Day 15 | Prompt tuning difficulty | Improved LLM prompts
Sprint 5 | Day 20 | RAG integration complexity | Implemented FAISS with simple embeddings
Sprint 6 | Day 25 | Chart visualization issues | Used Recharts for better UI
Sprint 7 | Day 30 | Alert triggering logic | Added threshold-based alerts

## Retrospective
Sprint | Start Date | End Date | Team Member | Start Doing | Stop Doing | Continue Doing | Action Taken
Sprint 1 | Week 1 | Week 2 | Jaya Varsini | Planning tasks clearly | Overthinking UI | Learning React | Improved planning
Sprint 2 | Week 3 | Week 4 | Jaya Varsini | Writing modular backend code | Delaying testing | API development | Completed backend setup
Sprint 3 | Week 5 | Week 6 | Jaya Varsini | AI integration | Ignoring edge cases | Debugging | Improved scoring accuracy
Sprint 4 | Week 7 | Week 8 | Jaya Varsini | Deployment readiness | Late fixes | Testing | Successfully deployed